## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1+A2:D15 | S1 | US-01 | Understand the project objective,expected outcomes so that the overall system purpose is clear and project setup was done | MUST HAVE | None | Shamrutha | 3- Completed
S1 | S1 | US-02 | Explore basic stock market concepts such as stocks, indicators, and trading flow so that project-related discussions can be followed. | SHOULD HAVE | None | Shamrutha | 3- Completed
S2 | S2 | US-03 | Explore datasets, APIs, and data sources used in stock market projects so that data handling requirements are understood. | MUST HAVE | None | Shamrutha | 3- Completed
S2 | S2 | US-04 | Learn about supporting tools such as Figma, API keys, charts, ML basics, and backtesting concepts so that system components are familiar. | SHOULD HAVE | None | Shamrutha | 3- Completed
S3 | S3 | US-05 | Analyze dashboard requirements to understand what data, features, and visual elements should be displayed. | MUST HAVE | US-01, US-04 | Shamrutha | 3- Completed
S3 | S3 | US-06 | Evaluate different dashboard frameworks and finalize Streamlit as the most suitable option for implementation. | MUST HAVE | US-05 | Shamrutha | 3- Completed
S4 | S4 | US-07 | Learn Streamlit fundamentals and visualization techniques so that interactive dashboards can be developed. | MUST HAVE | US-06 | Shamrutha | 3- Completed
S4 | S4 | US-08 | Create mini dashboard prototypes using sample and Excel-based data to validate layout and visualization ideas. | MUST HAVE | US-07 | Shamrutha | 3- Completed
S5 | S5 | US-09 | Conduct discussions with ML and backtesting teams to finalize dashboard features such as AI signals, confidence scores, and metrics. | MUST HAVE | US-08 | Shamrutha | 3- Completed
S5 | S5 | US-10 | Refine the dashboard structure based on team inputs so that all required outputs can be accommodated. | MUST HAVE | US-09 | Shamrutha | 3- Completed
S6 | S6 | US-11 | Integrate ML outputs such as AI trading signals and confidence levels into the dashboard. | MUST HAVE | ML Team | Shamrutha | 3- Completed
S6 | S6 | US-12 | Integrate backtesting outputs including trading metrics, logs, and performance indicators into the dashboard. | MUST HAVE | Backtesting Team | Shamrutha | 3- Completed
S7 | S7 | US-13 | Integrate alert functionality into the dashboard so that important trading events are highlighted. | MUST HAVE | Backtesting Team | Shamrutha | 3- Completed
S8 | S8 | US-14 | Create a demo video showcasing dashboard features, integrations, charts, signals, and alerts for project presentation. | SHOULD HAVE | None | Shamrutha | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 95 | 69 | 57 | 40 | 32 | 17 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.1 | Understand project objective and overall workflow | Day 1 | Day 2 | Shamrutha | Learning | Completed | 6 | 6 | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T1.2 | Learn basic stock market concepts and indicators | Day 2 | Day 3 | Shamrutha | Learning | Completed | 5 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T2.1 | Explore datasets, APIs, and data sources | Day 3 | Day 4 | Shamrutha | Research | Completed | 6 | 4 | 3 | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T2.2 | Learn Figma, API keys, charts, ML & backtesting basics | Day 4 | Day 5 | Shamrutha | Research | Completed | 6 | 6 | 4 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T3.1 | Analyze dashboard requirements and expected features | Day 1 | Day 2 | Shamrutha | Analysis | Completed | 7 | 3 | 5 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T3.2 | Compare dashboard frameworks and finalize Streamlit | Day 2 | Day 3 | Shamrutha | Analysis | Completed | 5 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T4.1 | Learn Streamlit components and visualization techniques | Day 1 | Day 3 | Shamrutha | Learning | Completed | 7 | 4 | 5 | 2 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T4.2 | Create mini dashboards using sample & Excel data | Day 3 | Day 5 | Shamrutha | Development | Completed | 8 | 6 | 0 | 4 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T5.1 | Discuss dashboard features with ML & backtesting teams | Day1 | Day 2 | Shamrutha | Discussion | Completed | 4 | 3 | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T5.2 | Refine dashboard structure based on team inputs | Day 2 | Day 4 | Shamrutha | Development | Completed | 6 | 2 | 2 | 2 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T6.1 | Integrate ML signals and confidence levels | Day 1 | Day 3 | Shamrutha | Development | Completed | 7 | 6 | 3 | 5 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T6.2 | Integrate backtesting metrics and logs | Day 3 | Day 5 | Shamrutha | Development | Completed | 8 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T7.1 | Implement alert display in the dashboard | Day1 | Day 3 | Shamrutha | Development | Completed | 6 | 3 | 4 | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T7.2 | Fix UI issues and improve dashboard usability | Day 3 | Day 5 | Shamrutha | Testing | Completed | 5 | 4 | 5 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T8.1 | Resolve final integration issues and polish dashboard | Day1 | Day 3 | Shamrutha | Testing | Completed | 5 | 5 | 3 | 3 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T8.2 | Submission PPT,Demo Video,Documentation,Project | Day 3 | Day 5 | Shamrutha | Review | Completed | 4 | 3 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Lack of clarity on project objectives and end-to-end workflow | Conducted mentor discussion and reviewed project documentation
Sprint 1 | Day 8 | Difficulty understanding stock market concepts and indicators | R&D done and clarified doubts in team discussion
Sprint 2 | Day 14 | Confusion regarding datasets, APIs, and data availability | Explored sample datasets and reviewed API documentation
Sprint 2 | Day 18 | Unclear understanding of how ML and backtesting outputs would be used | Discussed high-level data flow with team and aligned expectations
Sprint 3 | Day 23 | Difficulty finalizing dashboard features and layout | Reviewed sample dashboards and finalized feature list
Sprint 4 | Day 31 | Initial challenges while learning Streamlit components | Practiced mini examples and referred Streamlit documentation
Sprint 5 | Day 40 | Delay in receiving finalized ML outputs | Used mock and sample data to continue dashboard development
Sprint 6 | Day 48 | Integration issues between dashboard and backtesting metrics | Coordinated with backtesting team and standardized data formats
Sprint 7 | Day 52 | UI inconsistencies and performance issues in visualizations | Refined layout and optimized chart rendering
Sprint 8 | Day 57 | Time constraints for demo video and documentation | Planned tasks efficiently and collaborated to complete final deliverables

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-26 | 2025-12-02 | Samruddhi Junavane,Polipalli Sai,Tarun,Shamrutha | Reviewing project documentation and understanding stock market basics | Assuming requirements without clarification | Participating in mentor and team discussions | Conducted requirement clarification session and aligned on project scope
2 | Sprint 2 | 2025-12-03 | 2025-12-09 | Tarun | Structuring Agile stories and sprint timelines | Writing vague or task-level stories | Following Agile methodology consistently | Refined user stories using MOSCOW prioritization
3 | Sprint 3 | 2025-12-10 | 2025-12-16 | Tarun,Polipalli Sai,Samruddhi Junavane,Shamrutha | Setting up Streamlit dashboard and Python environment | Delaying UI testing | Practicing incremental coding and testing | Successfully completed environment setup and basic dashboard layout
4 | Sprint 4 | 2025-12-17 | 2025-12-23 | Tarun,Samruddhi Junavane,Shamrutha | Integrating sample stock data and visualizations | Waiting for finalized ML outputs | Coordinating with ML and backtesting teams | Used mock data to complete dashboard visual components
5 | Sprint 5 | 2025-12-24 | 2025-12-30 | Tarun | Integrating ML Buy/Sell signals into dashboard | Hardcoding values in UI | Using dynamic and configurable data pipelines | Standardized ML signal format and integrated it into the dashboard
6 | Sprint 6 | 2025-12-31 | 2026-01-06 | Tarun,Shamrutha | Integrating alert functionality and trading notifications into the dashboard | Pushing changes without cross-team confirmation | Incremental testing after every integration | Resolved integration inconsistencies and stabilized dashboard features
7 | Sprint 7 | 2026-01-07 | 2026-01-13 | Tarun,Samruddhi Junavane,Shamrutha | Validating end-to-end data flow across all dashboard features | Ignoring minor UI inconsistencies | Peer reviews and team feedback sessions | Finalized feature set and prepared the system for demo and documentation
8 | Sprint 8 | 2026-01-14 | 2026-01-28 | Shamrutha,Samruddhi Junavane,Pollipalli Sai | Demo Video,Documentation,PPT | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission